Annex C

Areas of Excellence (AoE) Scheme

Procedural Guidelines to Universities and Project Teams on

Projects Funded in 2016/17 (Seventh Round)

Part I - General

- Please refer to the requirements set out in Part I – General of the Disbursement, Accounting and Monitoring Arrangements for Funding Schemes Administered by the Research Grants Council (DAMA).

Part II - Disbursement Arrangement

- The AoE grant is disbursed in the form of earmarked grants.  The University Grants Committee (UGC) Secretariat will arrange payment of grants in stages to the project team in accordance with the established procedures and the timetable of project implementation as endorsed by the UGC / Research Grants Council (RGC) before project commencement.  No virement from the grant to other projects / purposes is allowed.

Part III - Accounting Arrangement

Approved Scope

- It is the universities’ responsibilities to ensure that the UGC / RGC grants are used appropriately and reasonably within the approved scope and timeframe.  The AoE project grant from the RGC is, unless otherwise stated, a one-line vote without further division into sub-allocations.  Virement between approved budget items under the one-line vote within the same project does not require the RGC’s approval.  If a Project Coordinator (PC) wishes to spend the money on an item that is not covered by the approved budget, he / she has to seek prior approval from the RGC on the new item.

PC Allowance

- For projects funded in the 6th Round and onwards, annual allowance for PC is also provided to release / partly release the PC from normal teaching and administration duties to focus efforts on the research project.

Outsourcing of Research Work Outside Hong Kong

- Research grants for AoE projects awarded by the RGC should primarily be used in undertaking research work in Hong Kong by the PCs and their teams in order to train and groom research talents in Hong Kong.  It will be legitimate for the PCs to subcontract out a small part of the research work (regardless of geographic locations) only if all the following conditions are fully met:

- The proposed activity is a necessary and justified part of the research and has already been outlined in the approved proposal;

- The PCs should have identified and possessed a high level of research expertise in their teams when they submit research applications to the RGC.  The activity to be subcontracted out, for instance, data collection work, should not be the main intellectual focus of the research project;

- The persons / organisations providing the subcontracting services should be at arm’s length with the PCs or their serving universities (for instance, employees, friends, relatives, subsidiary companies, etc. should be avoided) and the procurement should be done in accordance with the university’s procedures and guidelines; and

- The PCs or their team members should be involved in monitoring the subcontracting services or the supervision of the subcontracting services.

- Any subcontracting services or research work to be conducted outside Hong Kong that were not included in the approved proposal will require RGC's prior approval.

On Approval of New Projects

- Universities are required to create a reserve account, to which unexpended grant balances of projects will be transferred at the end of the academic year, to be carried forward to the following year, or to the next triennium.

- For projects supported in the 4th Round and onwards, the UGC / RGC will conduct a major review on an AoE project before the end of the 4th year that would result in a recommendation on whether or not to continue funding for another four years, or a lesser period.  Requirements on university’s matching funding for projects funded in different rounds of AoE exercise are tabulated below:

| Exercise |  | University’s Matching Funding |
| --- | --- | --- |
| 4th & 5th Rounds | 1st Phase | - No mandatory requirement |
|  | 2nd Phase | - Mandatory matching funding#, in “real money”, for direct cost as committed by institutions and approved by the UGC / RGC |
| 6th Round | 1st Phase | - No mandatory requirement |
|  | 2nd Phase | - Tapered funding (50% of the 1st phase) with no mandatory matching funding requirement |
| 7th Round | 1st Phase | - Mandatory matching funding# of 10% of the total approved budget, in real money, for a funded project |
|  | 2nd Phase | - No mandatory requirement |

#	Provision and usage of matching funding should be reported in the progress / review / completion report of the project.

- In addition, universities should provide “in kind” contribution (e.g. research infrastructure, staff time for research etc.) throughout the project period.

- All newly approved projects should start within six months of the funding award.

On Termination / Completion of Projects

- Any unspent AoE project grant should be returned to the RGC upon completion / termination of the project.  In addition, the university concerned is required to return to the RGC the corresponding on-costs on a pro-rata basis (e.g. 15% of the unspent project grant for projects with on-costs rate at 15% for projects funded in the first five rounds if applicable, 18% for projects funded in the 6th round and 27% for projects funded in the 7th round).  The RGC will determine whether or not any of the PC allowance should be returned.

- For cases where the PC becomes ineligible for the grant (e.g. on prolonged leave / leaving Hong Kong / incapable of managing the project) prior to the completion of the project, the universities should endeavour to identify a suitable Co-Principle Investigator (Co-PI) / Co- Investigator (Co-I) who has been involved in the project since commencement or a suitable PC / Project Investigator to take over the role of PC and recommend to the RGC for approval.  Universities should notify the RGC as soon as the PC's departure / leave has been confirmed and the project account should be frozen at the same time.

- The following accounting rules should be observed in handling project termination:

- Once the project account is frozen, both the PC and the university are obliged to cease immediately committing or incurring new expenditures under the account except for committed and uncancellable normal expenditure of salary to Research Assistants or equivalent employed before project termination date for a reasonable but limited time (i.e. payment in lieu of notice when staff’s contracts have to be terminated as a result) and ordered equipment (where penalties are involved for cancellation of order).  Such expenses must be solely and directly related to the project in question and have been committed before the project account is frozen.

- Should the RGC eventually reject a PC’s request for change or temporary waiver of eligibility requirements and the date of termination takes retrospective effect from the commencement of PC's departure, leave or original completion date, the university is required to return the expenses incurred by the project starting from the retrospective termination date except under very exceptional and justifiable circumstances.

- Universities are required to return the unspent balance (and expenses incurred since the retrospective termination date if applicable) and submit a concluding report to the RGC within six months of termination.

- The RGC will consider the possible redeployment of the equipment acquired by RGC grants where necessary.  Exceptional cases will be considered by the RGC on their individual merits.

- The project account in respect of a completed project should be frozen immediately after the completion / termination date, and any request for additional expenses incurred after that date to the unspent balance of the project must not be entertained.  Under exceptional circumstances, universities are given the discretion to allow charging certain expenses shortly after the project completion date to the unspent project account in justified circumstances.  Before exercising such discretions, universities must satisfy themselves that the expenses are strictly necessary for dissemination of research results (e.g. attendance at important international conferences and essential publication work).  In any case, usage of unspent balance to meet the costs of purchase of stores / equipment or staff salaries beyond the project completion date is strictly prohibited.  Universities have the responsibility to ensure that the discretion is exercised only on an exceptional basis and should be prepared to provide full justifications on request by the RGC.

- It is the onus of universities to verify any claim of expenses incurred while the account is frozen and to satisfy themselves that due efforts have been made to ascertain whether to pay the expenses incurred after the project account has been frozen.  For audit and accountability purposes, the coordinating university and the PC are required to provide an itemized report of such expenses, together with corresponding justifications, in the relevant financial statement of the project.

- Upon completion / termination of a project, the coordinating university concerned is required to submit an audited financial statement to the RGC according to the format stipulated in the Notes for Auditors at Appendix.  The assurance report should be issued by independent auditors who must be certified public accountants holding a practising certificated registered under the Professional Accountants Ordinance (Cap. 50) (the Auditors).  The universities and project teams concerned are required to make available to the Auditors all information, invoices / receipts, documents and explanations relating to the projects.  Any unspent balance (and expenses incurred since the retrospective termination date if applicable) of the project grant, refund of indirect / on-costs should be returned, together with the audited financial statement, to the Secretariat within six months of project completion / termination.

- The RGC reserves the right to withdraw support and project grant for particular projects by giving appropriate advance notice.

Equipment

- Upon completion of the approved project, the equipment acquired can be redeployed at the discretion of the university.  Should an approved project be terminated for any reason, universities should report any major items of research equipment (costing $0.5 million and over) to the RGC.  The RGC reserves the right to redeploy any such major equipment acquired by the UGC grants for use by other universities where appropriate or practicable.

- Notwithstanding that the approved projects are fully funded or the equipment items have been included in the research proposals, the PCs and the universities must not use the UGC grants to purchase:

- personal electronic devices such as cell phones, tablets, iPod, iPad, MP3 players, digital cameras / video recorders and PDAs; and

- standard office equipment such as personal computers, servers, laptop computers, printers, scanners and standard software / software licence / dataset known to be available, or reasonably expected to be provided in the universities, except with sound justification as specially approved by the RGC.

Part IV - Monitoring Arrangement

- Genuine and deep collaboration is a very central notion of the AoE Scheme, and the university’s management should devote its utmost efforts to facilitate, expand and sustain the collaborative work in AoE projects.  For inter-university collaboration projects, documentation which sets out the extent of collaboration expected and required of all participants is necessary, and funding will be withdrawn if there are signs that genuine and deep collaboration is lacking.

Progress Reports

- Broadly speaking, the coordinating university is required to submit progress reports upon completion of each project stage or within 12 months of the commencement / last submission of the project, whichever is the earlier.  The timing for the fourth report has to be adjusted to tie in with the major review.  One soft copy (with the main report and attachment(s) in two separate files, in a CD-ROM or a USB memory stick) and three hard copies should be submitted.  If any project requires a longer time frame for preparation of reports, prior approval from the RGC must be sought.  The release of the next stage funding will be subject to satisfactory review of the previous project stage, and the related annual progress report must be submitted at least four months before the requested date for release of funding.  In normal circumstances, the review process will take about three months to complete, but it may take a longer time when site visits are conducted as and when necessary.

- The project implementation timetable endorsed by the RGC before project commencement is indicative and may be adjusted in the light of the actual progress of the project.  Nevertheless, the project team is responsible for ensuring that it has endeavoured to achieve the objectives and deliverables according to the timetable.

Reviews

- For projects funded in the 4th Round and onwards, a major review visit will be conducted by the Monitoring and Assessment (M&A) Panel Members before the end of the 4th year that would result in a recommendation on whether or not to continue funding for another four years, or a lesser period..  Additional visits may be proposed by the M&A Panel if needed.

- To enhance the monitoring process, if any major irregularity is observed by the M&A Panel, the PC concerned would be requested to present the project progress to the M&A Panel and the MPStC normally in June / December.  If necessary, a member of the respective M&A Panel may also visit the team as soon as a major irregularity is identified, say within six months, to ensure that timely rectification of the problem can be made.

### Completion Reports

- A full completion report should be submitted within 12 months of the approved project completion date.  One soft copy (with the main report and attachment(s) in two separate files, in a CD-ROM or a USB memory stick) and three hard copies should be submitted.  In the case where a project team has further updates on the research output of the project, they may submit the supplementary information after the submission of the completion report.  PCs are required to release the completion reports to the public through the RGC website.  Completion reports containing information such as abstract in non-technical terms, objectives, research output including the list of conference papers / publications / journals and research findings and contact information of PCs should be open to public access.  For projects funded in the 5th Round and onwards, the RGC will release the completion report and / or a summary of research results or findings to the public through internet or other means as deemed appropriate by the RGC.

- On public access of publications resulting from research funded by the RGC:

(a)	Upon acceptance of a paper for publication resulting from the work done on a research project funded in whole or in part by the RGC, the PC should check whether the publisher already allows (i) full open access to the publisher’s version, or (ii) the author’s depositing a copy of the paper (either the publisher’s version or the final accepted manuscript after peer-review) in the university’s repository for open access;

(b)	if both (a)(i) and (ii) are not allowed, the PC should request the publisher’s permission to place either version in his / her university’s repository for restricted access immediately upon publication or after an embargo period of up to twelve months if required by the publisher; and

(c)	subject to the publisher’s agreement on (a) or (b) above, the PC should deposit a copy of the publication in his / her university’s repository as early as possible but no later than six months after publication or the embargo period, if any.

- The PC is required to include in the completion report URL links to the university’s repository or the publishers’ websites so that the public can have quick and easy access to the manuscripts or journal articles (though the public may be required to subscribe at the publishers’ websites).  The PC is also encouraged to include in the completion report the data repositories where research data of the project can be accessed and shared.

## Unsatisfactory, Barely Satisfactory and Overdue Reports

- Timely submission of reports is important and reflects on the diligence and ability of the PC in managing a project.  If reports remain overdue by the submission deadline, the RGC will consider terminating the projects and rating them as ‘Unsatisfactory’ for record.  All records of RGC funded projects rated “Unsatisfactory” or “Barely Satisfactory”, regardless of whether they are for overdue or other reasons, may be taken into account when a PC’s new funding application is considered.  The overall grading of the PC’s funding application submitted to the new funding exercises may be downgraded.  For cases concerning non-submission and overdue submission of completion or progress reports, the PC may be debarred from applying for grants administered by the RGC for two years or until the submission of the outstanding report.  Normally, the “Unsatisfactory” and “Barely satisfactory” records would be disregarded by the selection panel three years after passing the judgement.

- The university should freeze the project account if any progress report of an on-going project is overdue.  In this regard, university should undertake thorough and timely checking on the submission of reports to the RGC, take immediate action to freeze the accounts of projects which have overdue progress reports and notify the RGC Secretariat of the action taken.

Change Request

- All change requests, including changes to the governance structure, project duration, project objectives, composition of the project team, budget plan for allocation of funding amongst the different participating UGC-funded universities, and use of funding in other jurisdictions exceeding the permissible amount (including outsourcing of research work outside Hong Kong), etc., require prior approval of the RGC.  Universities should submit the change request three months prior to the intended effective date of the change and separately from the submission of progress / review report.  The change request will be handled in accordance with the following principles:

- Any proposed change(s) to the governance structure, including addition or withdrawal of coordinating or participating universities, will only be considered with strong justification.

- Requests for adjustment of the duration of each stage will be considered flexibly in order to enable the research to progress in a fruitful manner.  The basic principle remains that any further release of funding will be withheld if a project fails to attain sufficient and reasonable progress.  For projects which have received the last tranche of funding and are close to completion, any end-stage extension must not go beyond 12 months.

- Change of PC or Co-PIs will, as a matter of rule, not be allowed for the Start-up Stage.  For cases where the PC or a Co-PI leaves the project team after the Start-up Stage, a request for replacement of the PC / Co-PI may be considered if a suitable person can be identified to take over the role.  In examining such a request, the RGC will take into account the credential of the new team and its capability to carry on the research in a productive manner.  Prior approval of the RGC is required for change in project team composition.

- Universities have the primary responsibility to assist the project teams in whatever way practicable in order to make sure that the project is well managed and progress satisfactorily.  In this regard, the RGC expects that universities consider any request for changes in a serious light and, only when they are deemed justifiable, submit the request to the RGC for consideration.

- For other changes of a special nature but not mentioned above, they will be considered by the RGC on a case-by-case basis.

Time-commitment of the PCs

- To ensure that the PCs of major projects will spend reasonable time on project management, a PC of major projects (i.e. projects funded under the AoE and the Theme-based Research Scheme) should hold no more than two on-going projects at the same time.  The PC should spend sufficient time on the project throughout the project period.  The length of time spent should be commensurate with the PC allowance for a funded project to release / partly release the PC from normal teaching and administration duties to focus efforts on the research project.

- The PC should also report his / her efforts in project management in the progress / review / completion report forms.

Technology Transfer Plan

- For projects funded in 2014/15 academic year and onwards, PC who contemplates applying for funding support from the Innovation and Technology Fund at a later stage may provide a technology transfer plan, or an update of the plan previously submitted in the preliminary / full proposal, in the course of submitting progress / review report for advance information of the Innovation and Technology Commission.  This plan will not be assessed by the M&A Panel for the purpose of project monitoring and assessment.

Project Dissemination

- It is important that the achievements of the AoE projects could be communicated and shared amongst the research community and other stakeholders such as the general public, the relevant industrial sector and policy makers.  Universities should follow the endorsed project dissemination plan in communicating the project outcomes to the research community and the public.

- As an initiative to highlight the impact of the AoE Scheme on research and societal development in Hong Kong and worldwide, starting from the 7th Round exercise, the coordinating university of a funded project is required to provide a video clip on the research project and achievements to publicise the project’s research achievements within three months upon satisfactory rating of the completion report.  The video should be bilingual (e.g. English narration with Chinese subtitles or vice-versa) and lasts for about three minutes.  It will be vetted by the relevant M&A Panel.  The PCs of completed projects are also encouraged to upload the video clips onto their universities’ own websites or video channels.

Acknowledgement

- While the UGC / RGC will not claim copyright or other intellectual property right of the output produced, a suitable acknowledgement of the UGC / RGC funding should be included in any equipment / facilities purchased and any publication / publicity arising from the work done on the project funded in whole or in part by the RGC.  Where appropriate, royalty-free licenses for the use of the projects should be offered to all UGC-funded universities.  The following format of acknowledgement should be used:

“The work described in this paper (or “This equipment / facility) was fully / substantially / partially supported by a grant from the Research Grants Council of the Hong Kong Special Administrative Region, China (Project No. [AoE/[discipline]-[three-digit serial number]/[year], e.g. AoE/M-901/16]”.

- The above guidelines serve only to give a general framework for reference and are by no means exhaustive.  The RGC may at any time revise these guidelines.  Your Research Office will be notified of the change in due course.  In case of doubt, participating universities should check with the UGC Secretariat for clarification.  All communications must be routed through universities’ Research Offices, and the UGC Secretariat will in no circumstances entertain requests directly put forth by the project teams.

* * * * * * * * *

Research Grants Council

December 2016

For projects funded in the 6th Round and onwards, an annual allowance of up to a maximum of two-month average salary of a chair professor will be provided to each funded project to release / partly release the PC from his / her normal teaching and administration duties to focus his / her efforts on the research project.  The allowance will be disbursed to respective coordinating universities.